## Summary (hidden)
TPE Upgrade (December 1, 2021~November 30, 2022) | [6 empty] | Currency: USD
|  | Suppliers Payment Status |  |  | Parties Payment Status
UPG# | Billing Milestone /Description | Invoice | Amount Remitted by the CBP | Outstanding Amount | Invoice | Amount Received by the CBP | Outstanding Amount | Remark
9 | Purchasing Surplus Capacities (2x10G on DLS12) | TBC | TBC | TBC | #REF! | 39892.13 | #REF! | CBP received $39,892.13 from VERIZON for purchasing Surplus capacities(2x10G on DLS12), but Parties(CU/NTT/CHT) haven't claimed this payment($39,908.4)
10 | BM0, BM1, BM2, Taxes | 998554.56 | 998554.56 | 0 | 998554.56 | 1031718.2488 | 33163.6888 | KT's prepaid amount for UPG#10 BM3
11 | BM0 | 59620 | 59620 | 0 | 59620 | 59620 | 0
11 | BM1, BM2 | 440964 | 0 | -440964 | 440964 | 90563.02 | -350400.98 | Due Date: Dec.05(BM1) & Dec.12(BM2)
12 | BM0 | 214378.6 | 0 | -214378.6 | 214378.61 | 162991.06 | -51387.55 | Due Date: Dec.05
| Total: | 1713517.16 | 1058174.56 | -655342.6 | #REF! | 1384784.4588 | #REF!

## Report_MC#18 (hidden)
TPE Upgrade (December 1, 2021~November 30, 2022) | [13 empty] | Currency: USD
|  | Supplier Payment Status |  |  |  |  | Parties Payment Status
UPG# | Billing Milestone/Description | Suppliers | Amount of Invoice | Amount Remitted to Suppliers | Amount Outstanding | Due Date | Party | Invoice Ref. | Amount Billed | Amount Received | Amount Outstanding | Due Date | Received Date | Days Past Due | CBP's Account Balance
9 | Purchasing Surplus Capacities (2x10G on DLS12) | CU/NTT/CHT |  |  |  | TBC | VERIZON |  | #REF! | 39892.13 | #REF! | 2020-10-22 | 2020-10-22 | 0
9 | Purchasing Surplus Capacities | SUBTOTAL | 0 | 0 | 0 |  |  |  | #REF! | 39892.13 | #REF! |  |  |  | 39892.13 | CBP received $39,892.13 for purchasing Surplus capacities(2x10G on DLS12), but Parties(CU/NTT/CHT) haven't claimed this payment
10 | BM0 | CIENA | 103311 | 103311 | 0 | 2021-07-27 | KT | TPE-UPG10-KT-20210428 | 60765.7663 | 60765.7663 | 0 | 2021-05-21 | 2021-05-21 | 0
10 | BM0 | CHT | 6000 | 6000 | 0 | 2021-07-27 | CU | TPE-UPG10-CU-20210428 | 48545.2337 | 48545.2337 | 0 | 2021-05-21 | 2021-05-21 | 0
10 | BM0 | Total | 109311 | 109311 | 0 |  |  |  | 109311 | 109311 | 0
10 | BM1 | CIENA | 414336.76 | 414336.76 | 0 | 2021-10-28 | KT | TPE-UPG10-KT-20210908 | 234149.6611 | 234149.6611 | 0 | 2021-10-30 | 2021-10-01 | -29
10 | BM1 | CHT | 6000 | 6000 | 0 | 2021-10-28 | CU | TPE-UPG10-CU-20210908 | 186187.0989 | 186187.0989 | 0 | 2021-10-30 | 2021-10-21 | -9
10 | BM1 | Total | 420336.76 | 420336.76 | 0 |  |  |  | 420336.76 | 420336.76 | 0
10 | BM2 | CIENA | 413244 | 413244 | 0 | 2021-12-07 | KT | TPE-UPG10-KT-20211019 | 233056.9011 | 233056.9011 | 0 | 2021-12-18 | 2021-11-19 | -29
10 | BM2 | CHT | 6000 | 6000 | 0 | 2021-12-07 | CU | TPE-UPG10-CU-20211019 | 186187.0989 | 186187.0989 | 0 | 2021-12-18 | 2021-11-25 | -23
10 | BM2 | Total | 419244 | 419244 | 0 |  |  |  | 419244 | 419244 | 0
10 | Taxes | CIENA | 43662.8 | 43662.8 | 0 | 2022-03-21 | KT | TPE-UPG10-KT-20220118 | 27607.4512 | 60771.14 | 33163.6888 | 2022-03-16 | 2022-03-16 | 0
10 | Taxes | CHT | 6000 | 6000 | 0 | 2022-03-21 | CU | TPE-UPG10-CU-20220118 | 22055.3488 | 22055.3488 | 0 | 2022-03-16 | 2022-03-16 | 0
10 | Taxes | Total | 49662.8 | 49662.8 | 0 |  |  |  | 49662.8 | 82826.4888 | 33163.6888
10 |  | SUBTOTAL | 998554.56 | 998554.56 | 0 |  |  |  | 998554.56 | 1031718.2488 | 33163.6888 |  |  |  | 33163.6888 | KT's prepaid amount for UPG#10 BM3
11 | BM0 | CIENA | 53620 | 53620 | 0 | 2022-04-11 | KT | TPE-UPG11-KT-20220321 | 9936.6669 | 9936.6669 | 0 | 2022-04-25 | 2022-04-15 | -10
11 | BM0 | CHT | 6000 | 6000 | 0 | 2022-04-11 | CU | TPE-UPG11-CU-20220321 | 29810 | 29810 | 0 | 2022-04-25 | 2022-06-27 | 63
11 | BM0 | [5 empty] | CT | TPE-UPG11-CT-20221010 | 19873.3331 | 19873.3331 | 0 | 2022-04-25 | 2022-07-05 | 71
11 | BM0 | Total | 59620 | 59620 | 0 |  |  |  | 59620 | 59620 | 0
11 | BM1 | CIENA | 214482 | 0 | -214482 | 2022-12-09 | KT | TPE-UPG11-KT-20220701 | 36747 | 36747 | 0 | 2022-12-05 | 2022-08-26 | -101
11 | BM1 | CHT | 6000 | 0 | -6000 | 2022-12-09 | CU | TPEUPG11-CU-01 | 110241 | 0 | -110241 | 2022-12-05 | TBC | #VALUE!
11 | BM1 |  |  |  |  | 2022-12-09 | CT | TPEUPG11-CT-01 | 73494 | 0 | -73494 | 2022-12-05 | TBC | #VALUE!
11 | BM1 | Total | 220482 | 0 | -220482 |  |  |  | 220482 | 36747 | -183735
11 | BM2 | CIENA | 214482 | 0 | -214482 | 2022-12-28 | KT | TPE-UPG11-KT-20220701 | 36747 | 53816.02 | 17069.02 | 2022-12-12 | 2022-08-26 | -108
11 | BM2 | CHT | 6000 | 0 | -6000 | 2022-12-28 | CU | TPEUPG11-CT-02 | 110241 | 0 | -110241 | 2022-12-12 | TBC | #VALUE!
11 | BM2 | [5 empty] | CT | TPEUPG11-CT-02 | 73494 | 0 | -73494 | 2022-12-12 | TBC | #VALUE!
11 | BM2 | Total | 220482 | 0 | -220482 |  |  |  | 220482 | 53816.02 | -166665.98
11 |  | SUBTOTAL | 500584 | 59620 | -440964 |  |  |  | 500584 | 150183.02 | -350400.98 |  |  |  | 90563.02 | KT's prepaid amount for UPG#11
12 | BM0 | CIENA | 208378.6 | 0 | -208378.6 | 2022-12-15 | KT | TPEUPG12-KT-00 | 162991.06 | 162991.06 | 0 | 2022-12-05 | TBC | #VALUE!
12 | BM0 | CHT | 6000 | 0 | -6000 | 2022-12-15 | CU | TPEUPG12-CU-00 | 31467.81 | 0 | -31467.81 | 2022-12-05 | TBC | #VALUE!
12 | BM0 | [5 empty] | NTT-LJ | TPEUPG12-NTT-LJ-00 | 19919.74 | 0 | -19919.74 | 2022-12-05 | TBC | #VALUE!
12 | BM0 | Total | 214378.6 | 0 | -214378.6 |  |  |  | 214378.61 | 162991.06 | -51387.55
12 |  | SUBTOTAL | 214378.6 | 0 | -214378.6 |  |  |  | 214378.61 | 162991.06 | -51387.55 |  |  |  | 162991.06
|  | GRAND TOTAL |  | 1058174.56 | [5 empty] | 1384784.4588 |  |  |  |  | 326609.8988
Formulas:
Days Past Due = -DATEDIF([Received Date],[Due Date],"d")
Days Past Due = DATEDIF([Due Date],[Received Date],"d")
Note on C4: Pay to: CU $6,781.68 NTT $2,260.57 CHT $24,866.15 CHT $6,000 Total: $39,908.4
Note on L4: discrepancy $16.27: bank charges
Note on K15: KT's Prepayment ($60,771.14) of UPG#10
Note on L15: KT's balance amount after offetting prepayment $60,771.14
Note on K23: offset KT's prepayment ($90,563.02) of UPG#11 (BM1~3)
Note on K27: offset KT's prepayment ($90,563.02) of UPG#11 (BM1~3)
Note on L27: KT's balance amount of prepayment ($90,563.02) of UPG#11 after offsets

## theCBP books
| TPE UPG# |  | Suppliers' Invoice 供應商發票 |  |  |  | Parties's Share | [6 empty] | 會員帳單明細與付款資訊 | [8 empty] | Paid to Suppliers 匯出金額給供應商 |  |  |  | -649342.6
Report | UPG# | BM | Suppliers | Supplier's Invoice No. | Amt(USD) | Due Date | Party | Item | Supplier | Description | Supplier Billed Amt(US$) | Liability | Shared Amt (USD) | Invoice# (CBP to Party) | Party | Description | Amount Billed (USD) | Due Date | Received Date | Received Amt(USD) | Diff | Remark | Pay to Supplier | Amt (USD) | Remittance Date | Diff | Diff (Pay to Supplier VS) | Remark
v | 9 | BM0 | CIENA | 13040, 77367 | 41971.84 |  | KT | 1 | CIENA | BM0 |  |  | 820 | TPE-UPG9-KT-001 | KT | BM0 | 820 | 2020-10-22 | 2020-10-23 | 47966.64 | -5.2 |  | CIENA | 41971.84 | 2021-01-22 | 0 | #REF! | v
v | 9 | BM0 |  |  |  |  | KT | 2 | CIENA | BM0 |  |  | 41151.84 |  |  | BM0 | 41151.84 | 2020-10-22 | [7 empty] | 0 | NA | v
v | 9 | BM0 | CHT |  | 6000 |  | KT | 3 | CHT | CBP Fee |  |  | 6000 |  |  | CBP Fee | 6000 | 2020-10-22 |  |  |  |  | CHT | 6000 | 2021-01-22 | 0 | #REF! | v
v | 9 | BM1 | CIENA | 13062, 13184, 13185, 77416, 78448, 78449, 78657 | 385519.13 |  | KT | 1 | CIENA | BM1 |  |  | 167883 | TPE-UPG9-KT-001 | KT | BM1 | 167883 | 2020-11-30 | 2020-11-30 | 391513.91 | -5.22 |  | CIENA | 385519.13 | 2021-01-22 | 0 | #REF! | v
v | 9 | BM2 |  |  |  |  | KT | 2 | CIENA | BM2 |  |  | 167883.36 |  |  | BM2 | 167883.36 | 2020-11-30 | [7 empty] | 0 | NA | v
v | 9 | BM3 |  |  |  |  | KT | 3 | CIENA | BM3 |  |  | 41970.84 |  |  | BM3 | 41970.84 | 2020-11-30 | [7 empty] | 0 | NA | v
v | 9 | BM1~3 | CHT |  | 6000 |  | KT | 4 | CHT | CBP FEE |  |  | 6000 |  |  | CBP FEE | 6000 | 2020-11-30 |  |  |  |  | CHT | 18000 | 2021-01-22 | 12000 | #REF! | v
v | 9 | BM1~3 |  |  |  |  | KT | 5 | CIENA | Reimbursement of duty&tax for JAPAN |  |  | 7781.93 |  |  | Reimbursement of duty&tax for JAPAN | 7781.93 | 2020-11-30 | [7 empty] | 0 | NA | v
v | 9 | Surplus | CU |  | 6781.68 |  | VERIZON | 1 | CIENA | Surplus Capacity2*10G on DLS12(T4-T6) |  |  | 33908.4 | TPE-UPG9-CBP-Verrizon-01 | VERIZON (AT&T) | Surplus Capacity2*10G on DLS12(T4-T6) | 33908.4 | 2020-10-22 | 2020-10-23 | 39892.13 | -16.27 |  | CU | *6781.68 | TBC | -33908.4 | #VALUE! | ask 王凱, NTT
v | 9 | Surplus | NTT |  | 2260.5713 | [17 empty] | NTT | *2260.56 | TBC |  | #VALUE!
v | 9 | Surplus | CHT |  | 24866.1487 | [17 empty] | CHT | *24866.16 | TBC |  | #VALUE!
v | 9 | Surplus | CHT |  | 6000 |  | VERIZON | 2 | CHT | CBP Fee |  |  | 6000 |  |  | CBP Fee | 6000 | 2020-10-22 |  |  |  |  | CHT | *6000 | TBC | -6000 | #VALUE! | v
v | 10 | BM0 | CIENA | 13628, 80631 | 103311 |  | KT | 1 | CIENA | BM0-Contract Agreement |  |  | 1606.5452 | TPE-UPG10-KT-20210428 | KT | BM0-Contract Agreement | 1606.5452 | 2021-05-21 | 2021-05-21 | 60760.39 | -5.3763 | bank charge$5.38已加入下次invoice | CIENA | 103311 | 2021-07-27 | 0 | 0
v | 10 | BM0 |  |  |  |  | KT | 2 | CIENA | Tax of BM0 |  |  | 160.6545 |  |  | Tax of BM0 | 160.6545 | 2021-05-21 | [7 empty] | 0 | 0
v | 10 | BM0 |  |  |  |  | KT | 3 | CIENA | BM0-Contract Agreement |  |  | 55663.1785 |  |  | BM0-Contract Agreement | 55663.1785 | 2021-05-21 | [7 empty] | 0 | 0
v | 10 | BM0 | CHT |  | 6000 |  | KT | 4 | CHT | CBP Fee |  |  | 3335.388 |  |  | CBP Fee | 3335.388 | 2021-05-21 |  |  |  |  | CHT | 6000 | 2021-07-27 | 0 | 0
v | 10 | BM0 |  |  |  |  | CU | 1 | CIENA | BM0-Contract Agreement |  |  | 1283.4548 | TPE-UPG10-CU-20210428 | CU | BM0-Contract Agreement | 1283.4548 | 2021-05-21 | 2021-06-30 | 48514.84 | -30.3937 | bank charge$30.39已加入下次invoice |  |  |  | 0 | 0
v | 10 | BM0 |  |  |  |  | CU | 2 | CIENA | Tax of BM0 |  |  | 128.3455 |  |  | Tax of BM0 | 128.3455 | 2021-05-21 | [7 empty] | 0 | 0
v | 10 | BM0 |  |  |  |  | CU | 3 | CIENA | BM0-Contract Agreement |  |  | 44468.8215 |  |  | BM0-Contract Agreement | 44468.8215 | 2021-05-21 | [7 empty] | 0 | 0
v | 10 | BM0 |  |  |  |  | CU | 4 | CHT | CBP Fee |  |  | 2664.612 |  |  | CBP Fee | 2664.612 | 2021-05-21 | [7 empty] | 0 | 0
v | 10 | BM1 | CIENA | 14026, 83369 | 413244 |  | KT | 1 | CIENA | BM1-Contract Agreement |  |  | 6426.1809 | TPE-UPG10-KT-20210908 | KT | BM1-Contract Agreement | 6426.1809 | 2021-10-30 | 2021-10-01 | 234149.65 | -5.3911 | bank charge$5.39已加入下次invoice | CIENA | 414336.76 | 2021-10-28 | 1092.76 | 1092.76
v | 10 | BM1 |  |  |  |  | KT | 2 | CIENA | Tax of BM1 |  |  | 642.6181 |  |  | Tax of BM1 | 642.6181 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 |  |  |  |  | KT | 3 | CIENA | BM1-Contract Agreement |  |  | 222652.7141 |  |  | BM1-Contract Agreement | 222652.7141 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 | CIENA | 7222531, 7222532, 7704308 | 1092.76 |  | KT | 4 | CIENA | JAPAN CONSUMPTION TAX |  |  | 1092.76 |  |  | JAPAN CONSUMPTION TAX | 1092.76 | 2021-10-30 | [7 empty] | -1092.76 | -1092.76
v | 10 | BM1 |  |  |  |  | KT | [8 empty] | Bank Charges For BM0 | 5.38 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 | CHT |  | 6000 |  | KT | 6 | CHT | CBP Fee |  |  | 3335.388 |  |  | CBP Fee | 3335.388 | 2021-10-30 |  |  |  |  | CHT | 6000 | 2021-10-28 | 0 | 0
v | 10 | BM1 |  |  |  |  | CU | 1 | CIENA | BM1-Contract Agreement |  |  | 5133.8191 | TPE-UPG10-CU-20210908 | CU | BM1-Contract Agreement | 5133.8191 | 2021-10-30 | 2021-10-21 | 186202.1 | -15.3889 | bank charge$15.39已加入下次invoice |  |  |  | 0 | 0
v | 10 | BM1 |  |  |  |  | CU | 2 | CIENA | Tax of BM1 |  |  | 513.3819 |  |  | Tax of BM1 | 513.3819 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 |  |  |  |  | CU | 3 | CIENA | BM1-Contract Agreement |  |  | 177875.2859 |  |  | BM1-Contract Agreement | 177875.2859 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 |  |  |  |  | CU | [8 empty] | Bank Charges For BM0 | 30.39 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM1 |  |  |  |  | CU | 5 | CHT | CBP Fee |  |  | 2664.612 |  |  | CBP Fee | 2664.612 | 2021-10-30 | [7 empty] | 0 | 0
v | 10 | BM2 | CIENA | 83967, 14185 | 413244 |  | KT | 1 | CIENA | BM2-TSEs Factory Release |  |  | 6426.1809 | TPE-UPG10-KT-20211019 | KT | BM2-TSEs Factory Release | 6426.1809 | 2021-12-18 | 2021-11-19 | 233056.88 | -5.4111 | bank charge$5.41已加入下次invoice | CIENA | 413244 | 2021-12-07 | 0 | 0
v | 10 | BM2 |  |  |  |  | KT | 2 | CIENA | Tax of BM2 |  |  | 642.6181 |  |  | Tax of BM2 | 642.6181 | 2021-11-19 | [7 empty] | 0 | 0
v | 10 | BM2 |  |  |  |  | KT | 3 | CIENA | BM2-TSEs Factory Release |  |  | 222652.7141 |  |  | BM2-TSEs Factory Release | 222652.7141 | 2021-11-19 | [7 empty] | 0 | 0
v | 10 | BM2 |  |  |  |  | KT | [8 empty] | Bank Charges For BM1 | 5.39 | 2021-11-19 | [7 empty] | 0 | 0
v | 10 | BM2 | CHT |  | 6000 |  | KT | 5 | CHT | CBP Fee |  |  | 3335.388 |  |  | CBP Fee | 3335.388 | 2021-11-19 |  |  |  |  | CHT | 6000 | 2021-12-07 | 0 | 0
v | 10 | BM2 |  |  |  |  | CU | 1 | CIENA | BM2-TSEs Factory Release |  |  | 5133.8191 | TPE-UPG10-CU-20211019 | CU | BM2-TSEs Factory Release | 5133.8191 | 2021-12-18 | 2021-11-25 | 186187.08 | -15.4089 | bank charge$15.41已加入下次invoice |  |  |  | 0 | 0
v | 10 | BM2 |  |  |  |  | CU | 2 | CIENA | Tax of BM2 |  |  | 513.3819 |  |  | Tax of BM2 | 513.3819 | 2021-12-18 | [7 empty] | 0 | 0
v | 10 | BM2 |  |  |  |  | CU | 3 | CIENA | BM2-TSEs Factory Release |  |  | 177875.2859 |  |  | BM2-TSEs Factory Release | 177875.2859 | 2021-12-18 | [7 empty] | 0 | 0
v | 10 | BM2 |  |  |  |  | CU | [8 empty] | Bank Charges For BM1 | 15.39 | 2021-12-18 | [7 empty] | 0 | 0
v | 10 | BM2 |  |  |  |  | CU | 5 | CHT | CBP Fee |  |  | 2664.612 |  |  | CBP Fee | 2664.612 | 2021-12-18 | [7 empty] | 0 | 0
v | 10 | Taxes | CIENA | 85186 | 42646.84 | 2022-03-21 | KT | 1 | CIENA | Reimbursement of taxes for Japan/Taiwan/China |  |  | 23707.2931 | TPE-UPG10-KT-20220118 | KT | Reimbursement of taxes for Japan/Taiwan/China | 23707.2931 | 2022-03-08 | 2022-03-16 | 27618.2112 | 0 |  | CIENA | 43662.8 | 2022-03-21 | 1015.96 | 1015.96
v | 10 | Taxes | CIENA | 7266312 | 507.98 | 2022-03-21 | KT | 2 | CIENA | tax(NTK538UN/NTNM70FB/NTK538UN) |  |  | 282.3851 |  |  | tax | 564.7701 | [5 empty] | CIENA |  |  | -507.98 | -507.98
v | 10 | Taxes | CIENA | 7266313 | 507.98 | 2022-03-21 | KT | 3 | CIENA | tax(S74-LIC-NTK560DQ) |  |  | 282.3851 | [9 empty] | CIENA |  |  | -507.98 | -507.98
v | 10 | Taxes | [13 empty] | Bank Charges For BM2 | 5.41 | 2022-03-08 | [7 empty] | 0 | 0
v | 10 | Taxes | [13 empty] | Bank Charges For Reimbursement | 5.35 | 2022-03-08 | [7 empty] | 0 | 0
v | 10 | Taxes | CHT |  | 6000 | 2022-03-21 | KT | 5 | CHT | CBP Fee |  |  | 3335.388 |  |  | CBP Fee | 3335.388 | 2022-03-08 |  |  |  |  | CHT | 6000 | 2022-03-21 | 0 | 0
| 10 | Taxes | [11 empty] | Pre-paid | KT |  |  |  |  | 33152.9288 | [5 empty] | 0 | 0
v | 10 | Taxes |  |  |  |  | CU | 1 | CIENA | Reimbursement of taxes for Japan/Taiwan/China |  |  | 18939.5469 | TPE-UPG10-CU-20220118 | CU | Reimbursement of taxes for Japan/Taiwan/China | 18939.5469 | 2022-03-08 | 2022-03-16 | 22070.48 | -0.26894 |  |  |  |  | 0 | 0
v | 10 | Taxes |  |  |  |  | CU | 2 | CIENA | tax(NTK538UN/NTNM70FB/NTK538UN) |  |  | 225.5949 |  |  | tax | 451.18 | [8 empty] | 0 | 0
v | 10 | Taxes |  |  |  |  | CU | 3 | CIENA | tax(S74-LIC-NTK560DQ) |  |  | 225.5949 | [12 empty] | 0 | 0
v | 10 | Taxes | [13 empty] | Bank Charges For BM2 | 15.41 | 2022-03-08 | [7 empty] | 0 | 0
v | 10 | Taxes |  |  |  |  | CU | 5 | CHT | CBP Fee |  |  | 2664.612 |  |  | CBP Fee | 2664.612 | 2022-03-08 | [7 empty] | 0 | 0
v | 11 | BM0 | CIENA | 500997, 14308 | 53620 | 2022-04-11 | KT | 1 | CIENA | BM0-Contract Agreement |  |  | 1012 | TPE-UPG11-KT-20220321 | KT | BM0-Contract Agreement | 1012 | #REF! | 2022-04-15 | 9931.5 | -5.1669 |  | CIENA | 53620 |  | 0 | 0
v | 11 | BM0 |  |  |  |  | KT | 2 | CIENA | BM0-Contract Agreement |  |  | 7924.6668 |  |  | BM0-Contract Agreement | 7924.6668 | #REF! | [7 empty] | 0 | 0
v | 11 | BM0 | CHT | xxxx | 6000 | 2022-04-11 | KT | 3 | CHT | CBP Fee |  |  | 1000 |  |  | CBP Fee | 1000 | #REF! |  |  |  |  | CHT | 6000 |  | 0 | 0
v | 11 | BM0 |  |  |  |  | CU | 1 | CIENA | BM0-Contract Agreement |  |  | 3036 | TPE-UPG11-CU-20220321 | CU | BM0-Contract Agreement | 3036 | #REF! | 2022-06-27 | 29794.92 | -15.08 | bank charge $15.08 已加入下次的invoice |  |  |  | 0 | 0
v | 11 | BM0 |  |  |  |  | CU | 2 | CIENA | BM0-Contract Agreement |  |  | 23774 |  |  | BM0-Contract Agreement | 23774 | #REF! | [7 empty] | 0 | 0
v | 11 | BM0 |  |  |  |  | CU | 3 | CHT | CBP Fee |  |  | 3000 |  |  | CBP Fee | 3000 | #REF! | [7 empty] | 0 | 0
v | 11 | BM0 |  |  |  |  | CT | 1 | CIENA | BM0-Contract Agreement |  |  | 2024 | TPE-UPG11-CT-20221010 | CT | BM0-Contract Agreement | 2024 | #REF! | 2022-07-05 | 19858.28 | -15.0531 | bank charge $15.05 已加入下次的invoice |  |  |  | 0 | 0
v | 11 | BM0 |  |  |  |  | CT | 2 | CIENA | BM0-Contract Agreement |  |  | 15849.3332 |  |  | BM0-Contract Agreement | 15849.3332 | #REF! | [7 empty] | 0 | 0
v | 11 | BM0 |  |  |  |  | CT | 3 | CHT | CBP Fee |  |  | 2000 |  |  | CBP Fee | 2000 | #REF! | [7 empty] | 0 | 0
| 11 | BM1 | CIENA | 503041 | 190194 | #REF! | CU | 1 | CIENA | BM1: Contract Agreement | 190194 | 50% | 95097 | TPEUPG11-CU-0110 | CU | BM1: Contract Agreement | 95097 | 2022-12-05 | 2022-12-05 | 110241.17 | -14.91 |  |  |  |  | -190194 | -190194
| 11 | BM1 | CIENA | 15328 | 22080 | 2022-12-09 | CU | 2 | CIENA | BM1: Contract Agreement | 22080 | 50% | 11040 |  |  | BM1: Contract Agreement | 11040 | [8 empty] | -22080 | -22080
| 11 | BM1 | CIENA | 15328 | 2208 | 2022-12-09 | CU | 3 | CIENA | Services Tax of Japan | 2208 | 50% | 1104 |  |  | Services Tax of Japan | 1104 | [8 empty] | -2208 | -2208
| 11 | BM1 | CHT | TPE-UPG11-221021 | 6000 | 2022-12-09 | CU | 4 | CHT | CBP Fee for UPG#11 (BM1) | 6000 | 50% | 3000 |  |  | CBP Fee for UPG#11 (BM1) | 3000 | [8 empty] | -6000 | -6000
| 11 | BM1 |  |  |  |  | CU | [8 empty] | Bank Charges For BM0 | 15.08 | [8 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | CT | 1 | CIENA | BM1: Contract Agreement | 190194 | 33.33% | 63398 | TPEUPG11-CT-01 | CT | BM1: Contract Agreement | 63398 | 2022-12-05 |  |  | -73509.05 | James Chu 褚彭魁: under internal approval 11/29: sent notice, awaiting for payment schedule |  |  |  | 0 | 0
| 11 | BM1 |  |  |  |  | CT | 2 | CIENA | BM1: Contract Agreement | 22080 | 33.33% | 7360 |  |  | BM1: Contract Agreement | 7360 | [8 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | CT | 3 | CIENA | Services Tax of Japan | 2208 | 33.33% | 736 |  |  | Services Tax of Japan | 736 | [8 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | CT | 4 | CHT | CBP Fee for UPG#11 (BM1) | 6000 | 33.33% | 2000 |  |  | CBP Fee for UPG#11 (BM1) | 2000 | [8 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | CT | [8 empty] | Bank Charges For BM0 | 15.05 | [8 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | KT | 1 | CIENA | BM1: Contract Agreement | 190194 | 16.67% | 31699 | TPE-UPG11-KT-20220701 | KT | BM1: Contract Agreement | 35379 | 2022-12-05 | 2022-08-26 | 35379 | 0 | 從預付$90,563.02中扣除 |  |  |  | 0 | 0 | KT prepaid: 90563.02
| 11 | BM1 |  |  |  |  | KT | 2 | CIENA | BM1: Contract Agreement | 22080 | 16.67% | 3680 |  |  | BM1: Contract Agreement | 3537.9 |  |  | 3537.9 | [5 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | KT | 3 | CIENA | Services Tax of Japan | 2208 | 16.67% | 368 | [12 empty] | 0 | 0
| 11 | BM1 |  |  |  |  | KT | 4 | CHT | CBP Fee for UPG#11 (BM1) | 6000 | 16.67% | 1000 |  |  | CBP Fee for UPG#11 (BM1) | 1000 |  |  | 1000 | [5 empty] | 0 | 0
| 11 | BM1 | [13 empty] | Credit Note for BM1 | -3169.9 |  |  | -3169.9 | [5 empty] | 0 | 0
| 11 | BM2 | CIENA | 503418 | 190194 | 2022-12-28 | CT | 1 | CIENA | BM2: Contract Agreement | 190194 | 33.33% | 63398 | TPEUPG11-CT-02 | #REF! | BM2: Contract Agreement | 63398 | #REF! |  |  | -73494 | James Chu 褚彭魁: invoices are received |  |  |  | -190194 | -190194
| 11 | BM2 | CIENA | 15428 | 22080 | 2022-12-28 | CT | 2 | CIENA | BM2: Contract Agreement | 22080 | 33.33% | 7360 |  |  | BM2: Contract Agreement | 7360 | [8 empty] | -22080 | -22080
| 11 | BM2 | CIENA | 15428 | 2208 | 2022-12-28 | CT | 3 | CIENA | Services Tax of Japan | 2208 | 33.33% | 736 |  |  | Services Tax of Japan | 736 | [8 empty] | -2208 | -2208
| 11 | BM2 | CHT | TPE-UPG11-221102 | 6000 | 2022-12-22 | CT | 4 | CHT | CBP Fee for UPG#11 (BM2) | 6000 | 33.33% | 2000 |  |  | CBP Fee for UPG#11 (BM2) | 2000 | [8 empty] | -6000 | -6000
| 11 | BM2 |  |  |  |  | CU | 1 | CIENA | BM2: Contract Agreement | 190194 | 50% | 95097 | TPEUPG11-CU-02 | #REF! | BM2: Contract Agreement | 95097 | #REF! | 2022-12-28 | 110226.11 | -14.89 |  |  |  |  | 0 | 0
| 11 | BM2 |  |  |  |  | CU | 2 | CIENA | BM2: Contract Agreement | 22080 | 50% | 11040 |  |  | BM2: Contract Agreement | 11040 | [8 empty] | 0 | 0
| 11 | BM2 |  |  |  |  | CU | 3 | CIENA | Services Tax of Japan | 2208 | 50% | 1104 |  |  | Services Tax of Japan | 1104 | [8 empty] | 0 | 0
| 11 | BM2 |  |  |  |  | CU | 4 | CHT | CBP Fee for UPG#11 (BM2) | 6000 | 50% | 3000 |  |  | CBP Fee for UPG#11 (BM2) | 3000 | [8 empty] | 0 | 0
| 11 | BM2 |  |  |  |  | KT | 1 | CIENA | BM2: Contract Agreement | 190194 | 16.67% | 31699 | TPE-UPG11-KT-20220701 | KT | BM2: Contract Agreement | 35379 | 2022-12-12 | 2022-08-26 | 35379 | 0 | 從預付$90,563.02中扣除 |  |  |  | 0 | 0
| 11 | BM2 |  |  |  |  | KT | 2 | CIENA | BM2: Contract Agreement | 22080 | 16.67% | 3680 |  |  | BM2: Contract Agreement | 3537.9 |  |  | 3537.9 | [5 empty] | 0 | 0
| 11 | BM2 |  |  |  |  | KT | 3 | CIENA | Services Tax of Japan | 2208 | 16.67% | 368 | [12 empty] | 0 | 0
| 11 | BM2 |  |  |  |  | KT | 4 | CHT | CBP Fee for UPG#11 (BM2) | 6000 | 16.67% | 1000 |  |  | CBP Fee for UPG#11 (BM2) | 1000 |  |  | 1000 | [5 empty] | 0 | 0
| 11 | BM2 | [13 empty] | Credit Note for BM2 | -3169.9 |  |  | -3169.9 | [5 empty] | 0 | 0
| 11 | BM3 |  |  |  |  | KT | 1 | [5 empty] | TPE-UPG11-KT-20220701 | KT | #REF! | 8844.67 | 2022-11-29 | 2022-08-26 | 8844.67 | -5.02 | 從預付$90,563.02中扣除 |  |  |  | 0 | 0
| 11 | BM3 |  |  |  |  | KT | 2 | [7 empty] | #REF! | 884.47 |  |  | 884.47 | [5 empty] | 0 | 0
| 11 | BM3 |  |  |  |  | KT | 3 | [7 empty] | #REF! | 1000 |  |  | 1000 | [5 empty] | 0 | 0
| 11 | BM3 |  |  |  |  | KT | 4 | [7 empty] | #REF! | 5.1 |  |  | 0.08 | [5 empty] | 0 | 0
| 11 | BM3 |  |  |  |  | KT | [7 empty] | KT | Credit Note for BM3 | 6339.8 | TBC |  | 6339.8 | 0 |  |  |  |  | 0 | 0
| 11 | BM1~3 |  |  |  |  | KT | [7 empty] | KT | Bank Charges For BM1~3 | 5.02 |  |  |  | -5.02 |  |  |  |  | 0 | 0
| 11 | BM1~3 |  |  |  |  | KT | [7 empty] | KT | Bank Charges For BM0 | 5.17 |  |  |  | -5.17 |  |  |  |  | 0 | 0
| 11 | BM3 |  |  |  |  | CT | [7 empty] | #REF! | Bank Charges For BM1~2 | TBC | TBC |  | TBC | TBC |  |  |  |  | 0 | 0
| 11 | BM3 |  |  |  |  | CU | [7 empty] | #REF! | Bank Charges For BM1~2 | TBC |  |  | TBC | TBC |  |  |  |  | 0 | 0
| 12 | BM0 | CIENA-USA | 502646 | 163412.01 | #REF! | CU | 1 | CIENA-USA | BM0: Contract Agreement | 163412.01 | 14.68% | 23986.62 | TPEUPG12-CU-00 | CU | BM0: Contract Agreement | 23986.62 | #REF! | 2022-12-05 | 31452.9 | -14.91 |  | CIENA-USA | 145507.24 | 2022-11-30 | -17904.77 | -17904.77
| 12 | BM0 | CIENA-USA | 6903038 | 27487.59 | #REF! | CU | 2 | CIENA-USA | BM0: Contract Agreement | 27487.59 | 14.68% | 4034.8 |  |  | BM0: Contract Agreement | 4034.8 | [5 empty] | CIENA-USA | 45392.36 | 2022-12-29 | 17904.77 | 17904.77
| 12 | BM0 | CIENA-JP | 15088 | 15890 | #REF! | CU | 3 | CIENA-JP | BM0: Contract Agreement | 15890 | 14.68% | 2332.43 |  |  | BM0: Contract Agreement | 2332.43 | [5 empty] | CIENA-JP | 17479 | 2022-11-30 | 1589 | 1589
| 12 | BM0 | CIENA-JP | 15088 | 1589 | #REF! | CU | 4 | CIENA-JP | Services Tax of Japan | 1589 | 14.68% | 233.24 |  |  | Services Tax of Japan | 233.24 | [8 empty] | -1589 | -1589
| 12 | BM0 | CHT | TPE-UPG12-221021 | 6000 | #REF! | CU | 5 | CHT | CBP Fee for UPG#12 (BM0) | 6000 | 14.68% | 880.72 |  |  | CBP Fee for UPG#12 (BM0) | 880.72 | [5 empty] | CHT | 6000 | 帳號待確認 | 0 | 0
| 12 | BM0 |  |  |  |  | KT | 1 | CIENA | BM0: Contract Agreement | 163412.01 | 76.03% | 124241.4 | TPEUPG12-KT-00 | KT | BM0: Contract Agreement | 124241.4 | #REF! | 2022-11-23 | 162986.24 | -4.82 |  |  |  |  | 0 | -190899.6
| 12 | BM0 |  |  |  |  | KT | 2 | CIENA | BM0: Contract Agreement | 27487.59 | 76.03% | 20898.69 |  |  | BM0: Contract Agreement | 20898.69 | [8 empty] | 0 | -17479
| 12 | BM0 |  |  |  |  | KT | 3 | CIENA | BM0: Contract Agreement | 15890 | 76.03% | 12081.09 |  |  | BM0: Contract Agreement | 12081.09 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | KT | 4 | CIENA | Services Tax of Japan | 1589 | 76.03% | 1208.11 |  |  | Services Tax of Japan | 1208.11 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | KT | 5 | CHT | CBP Fee for UPG#12 (BM0) | 6000 | 76.03% | 4561.77 |  |  | CBP Fee for UPG#12 (BM0) | 4561.77 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | NTT-LJ | 1 | CIENA | BM0: Contract Agreement | 163412.01 | 9.292% | 15184 | TPEUPG12-NTT-LJ-00 | NTT-LJ | BM0: Contract Agreement | 15184 | #REF! | 2022-12-28 | 19903.84 | -15.9 |  |  |  |  | 0 | 0
| 12 | BM0 |  |  |  |  | NTT-LJ | 2 | CIENA | BM0: Contract Agreement | 27487.59 | 9.292% | 2554.11 |  |  | BM0: Contract Agreement | 2554.11 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | NTT-LJ | 3 | CIENA | BM0: Contract Agreement | 15890 | 9.292% | 1476.47 |  |  | BM0: Contract Agreement | 1476.47 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | NTT-LJ | 4 | CIENA | Services Tax of Japan | 1589 | 9.292% | 147.65 |  |  | Services Tax of Japan | 147.65 | [8 empty] | 0 | 0
| 12 | BM0 |  |  |  |  | NTT-LJ | 5 | CHT | CBP Fee for UPG#12 (BM0) | 6000 | 9.292% | 557.51 |  |  | CBP Fee for UPG#12 (BM0) | 557.51 | [8 empty] | 0 | 0
| 12 | BM1~3 |  |  |  |  | KT | 1 | CIENA | BM1A (Supply Contract Cost) | 948934 | 100% | 948934 | TPEUPG12-KT-01A1205 | KT | BM1A (Supply Contract Cost) | 1048388.77 | 2022-01-21 | 2022-12-16 | 1048383.88 | -4.89 | KT's pre-payment |  |  |  | 0 | 0
| 12 | [6 empty] | 2 | CIENA | BM1A (Non Supply Contract Cost) | 94893 | 100% | 94893 |  |  | BM1A (Non Supply Contract Cost) | [9 empty] | 0 | 0
| 12 | [6 empty] | 3 | CHT | CBP Fee for BM1A | 6000 | 76.03% | 4561.77 |  |  | CBP Fee for BM1A | [9 empty] | 0 | 0
[5 empty] | 1753425.56 | [7 empty] | 2801814.34 |  |  |  | 2819011.4101 |  |  | 2704946.55 | -96867.79 |  |  | 1272553.16 |  | -480872.4
[16 empty] | Diff (A) | 17197.0701 |  |  | -96867.79 |  |  |  |  | Need to Pay | -33908.4
[16 empty] | Bank Charge | 123.04 |  |  | 17197.0701 | 17197.0701 |  |  |  | A/R | -440964
[16 empty] | KT's Proforma Invoice(#11 BM3) -- (3) | 17074.04 |  |  | #REF! | #REF! |  |  |  | Need to Check | 1015.96
[16 empty] | Balance | -0.0098679 |  |  | -129.2089 | -129.2089 |  |  |  |  | -7015.96
[20 empty] | 33152.9288 | 33152.9288
[20 empty] | #REF! | #REF!
[16 empty] | KT's Proforma Invoice (UPG#11) | 90568.04
[14 empty] | A/R |  | (1) BM1 | 0 |  |  | #REF!
[14 empty] | 2022-11-29 | UPG#11 BM1 | (2) BM2 | 0 |  |  | -14.91 | 11/30~12/9 Pay to Ciena
[16 empty] | (3) BM3-tbc | 17074.04 |  |  | -73509.05
[14 empty] | 2022-12-12 | UPG#11 BM2 | Balance | 73494 |  |  | -73494 | 12/13~28 Pay to Ciena
-14.89
[14 empty] | 2022-12-05 | UPG#12 BM0 |  |  |  |  | -14.91 | 12/6~15 Pay to Ciena
-4.82
-15.9
-15.21
#REF!
#REF!
Note on Y9: 多付了12000
Note on U11: received from AT&T
Note on Y23: 多付1092.76
Note on R97: UPG#11 1. CBP Received KT's prepaid of UPG#11: $90,563.02] 2. KT's Shared Amount of UPG#11: BM1: Shared Amount: $36,747 + Bank Charge for BM0 $5.17 = $36,752.17 BM2: Shared Amount: $36,747 + Bank Charge for BM1~3 $5.02 = $36,752.02 BM3:
Note on U139: UPG#11 1. CBP Received KT's prepaid of UPG#11(BM1~3): $90,563.02 2. KT's Shared Amount of UPG#11: BM1: Shared Amount: $36,747 + Bank Charge for BM0 $5.17 = $36,752.17 BM2: Shared Amount: $36,747 + Bank Charge for BM1~3 $5.02 = $36,752.02 BM3: TBC Balance: $17,058.83

## Prepaid balance
TPE Upgrade_Prepaid Balance_KT | [5 empty] | Currency: USD
UPG# | BM | Ref. No. | Description | Invoice Amount | Prepaid Amount | Balance
10 | BM3 |  | Prepaid amount |  | 60771.14 | 60771.14
10 | Taxes | TPE-UPG10-KT-20220118 | Reimbursement of taxes for Japan/Taiwan/China | 27607.4512 |  | 33163.6888
Sub-total Balance | [5 empty] | 33163.6888
UPG# | BM | Ref. No. | Description | Invoice Amount | Prepaid Amount | Balance
11 | BM1~3 |  | Prepaid amount |  | 90563.02 | 90563.02
11 | BM1 | TPE-UPG11-KT-20220701 |  | 36747 |  | 53816.02
11 | BM2 | TPE-UPG11-KT-20220701 |  | 36747 |  | 17069.02
Sub-total Balance | [5 empty] | 17069.02
UPG# | BM | Ref. No. | Description | Invoice Amount | Prepaid Amount | Balance
12 | BM1A |  | Prepaid amount for BM1A |  | 1048383.88 | 1048383.88
Sub-total Balance | [5 empty] | 1048383.88
|  |  |  | Total Balance |  | 1098616.5888

## Verizon's purchase (hidden)
Total | 33908.4
CU | 6781.68
NTT | 2260.5713
CHT | 24866.1487
6000

## 2145.80A明細109~111.11 (hidden)
[17 empty] | UPG#9 |  |  | UPG#9 (Surplus) |  | UPG#10 |  |  | UPG#11 |  |  | UPG#12
製票年度 | 機構代號 | 傳票種類 | 製票編號 | 列帳編號 | 列帳年度 | 列帳月份 | 列帳日 | 總帳 | 明細帳 | 輔助帳號 | 金額 | 借貸別 | 科目補充說明 | 外幣別 | 外幣金額 | 利息收入 | 收 | 付 |  | 收 | 付 | 收 | 付 |  | 收 | 付 |  | 收 | 付 | 摘要內容 | 會計經辦 | 淨額 | 會計項目
111 | 6060 | 4 | 2533 | 2546 | 111 | 7 | 25 | 2145 | 80A | TPE-2 | 177726 |  |  | US$ | 6000 | [14 empty] | 電匯VERIZON TPE海纜 UPG#7 NOC 工程代收款 | 閔秀英 | -177726 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 124 | 125 | 109 | 1 | 8 | 2145 | 80A | RATE12 | 866734 | - |  |  | 0 | [14 empty] | 迴轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 866734 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 343 | 301 | 109 | 1 | 15 | 2145 | 80A | TPE-2 | 1254163 | - | AT&T US$41,138.98(手續費US$16) | US$ | 41138.98 | [14 empty] | 代收TPE UPG#7 USD$41,138.98-AT&T | 閔秀英 | 1254163 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 345 | 303 | 109 | 1 | 15 | 2145 | 80A | TPE-2 | 3159477 | - | KT US$103,636.97(手續費US$5.03) | US$ | 103636.97 | [14 empty] | 代收TPE UPG#8 BM0 USD$103,636.97-KT | 閔秀英 | 3159477 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 573 | 543 | 109 | 1 | 31 | 2145 | 80A | RATE01 | 752014 |  |  |  | 0 | [14 empty] | TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | -752014 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 578 | 605 | 109 | 2 | 6 | 2145 | 80A | RATE01 | 752014 | - |  |  | 0 | [14 empty] | 迴轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 752014 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 585 | 626 | 109 | 2 | 6 | 2145 | 80A | TPE-2 | 88926 |  |  | US$ | 2952 | [14 empty] | 電匯 CIENA JAPAN TPE/UPG#7 BM2~3 工程代收款 | 閔秀英 | -88926 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 586 | 627 | 109 | 2 | 6 | 2145 | 80A | TPE-2 | 11884839 |  |  | US$ | 394530.57 | [14 empty] | 電匯CIENA US TPE/UPG7/BM2~3 UPG#8BM0工程代收款 | 閔秀英 | -11884839 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 587 | 628 | 109 | 2 | 6 | 2145 | 80A | TPE-2 | 542274 |  |  | US$ | 18001.39 | [14 empty] | 電匯 CHT TPE海纜UPG#7/BM2UPG#8/BM0作業手續費 | 閔秀英 | -542274 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 1148 | 1127 | 109 | 2 | 27 | 2145 | 80A | RATE02 | 750656 |  |  |  | 0 | [14 empty] | TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | -750656 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 1159 | 1165 | 109 | 3 | 4 | 2145 | 80A | RATE02 | 750656 | - |  |  | 0 | [14 empty] | 迴轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 750656 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 1746 | 1721 | 109 | 3 | 31 | 2145 | 80A | RATE03 | 762647 |  |  |  | 0 | [14 empty] | TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | -762647 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 1763 | 1769 | 109 | 4 | 7 | 2145 | 80A | RATE03 | 762647 | - |  |  | 0 | [14 empty] | 回轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 762647 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2247 | 2237 | 109 | 4 | 30 | 2145 | 80A | RATE04 | 995276 |  |  |  | 0 | [14 empty] | TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | -995276 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2248 | 2264 | 109 | 5 | 5 | 2145 | 80A | RATE04 | 995276 | - |  |  | 0 | [14 empty] | 回轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 995276 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2296 | 2268 | 109 | 5 | 5 | 2145 | 80A | TPE-2 | 3242261 | - | KT US$107,698.42(手續費US$5.04) | US$ | 107698.42 | [14 empty] | 代收TPE UPGRADE#8 BM2/BM3 款 -KT | 閔秀英 | 3242261 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2360 | 2402 | 109 | 5 | 12 | 2145 | 80A | TPE-2 | 3061783 |  |  | US$ | 101703.46 | [14 empty] | 電匯CIENA TPE/UPG#8 BM2~BM3工程代收款 | 閔秀英 | -3061783 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2763 | 2763 | 109 | 5 | 29 | 2145 | 80A | RATE05 | 861484 |  |  |  | 0 | [14 empty] | TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | -861484 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 2782 | 2802 | 109 | 6 | 4 | 2145 | 80A | RATE05 | 861484 | - |  |  | 0 | [14 empty] | 回轉TPE/TSE-1/NCP/CSCN/SJC2 海纜帳戶評價調整 | 閔秀英 | 861484 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 3194 | 3163 | 109 | 6 | 22 | 2145 | 80A | TPE-2 | 18246 | - |  | US$ | 616.82 | 616.82 | [13 empty] | 代收TPE UPG CBP利息收入(616.82) | 閔秀英 | 18246 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 5401 | 5361 | 109 | 10 | 23 | 2145 | 80A | TPE-2 | 1403744 | - | KT US$47,966.64(手續費US$5.20) | US$ | 47966.64 |  | 47966.64 | [12 empty] | 代收TPE 海纜 UPGRADE#9 工程款-KT | 閔秀英 | 1403744 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 6072 | 6060 | 109 | 11 | 30 | 2145 | 80A | TPE-2 | 11315535 | - | KT US$391,519.13(手續費US$5.22) | US$ | 391513.91 |  | 391513.91 | [12 empty] | 代收TPE 海纜 UPGRADE#9 工程款-KT | 閔秀英 | 11315535 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 6600 | 6554 | 109 | 12 | 22 | 2145 | 80A | TPE-2 | 3975 | - |  | US$ | 139.93 | 139.93 | [13 empty] | 代收TPE UPG CBP利息收入(139.93) | 閔秀英 | 3975 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 436 | 483 | 110 | 1 | 28 | 2145 | 80A | TPE-2 | 11915802 |  |  | US$ | 419289.97 |  |  | -419289.97 | BM0-BM3 | [10 empty] | 電匯CIENA US TPE海纜 UPG#9/BM0~3 工程代收款 | 閔秀英 | -11915802 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 439 | 484 | 110 | 1 | 28 | 2145 | 80A | TPE-2 | 233036 |  |  | US$ | 8200 |  |  | -8200 | BM0-BM3 | [10 empty] | 電匯CIENA JAPAN TPE海纜UPG#9 BM0~3工程代收款 | 閔秀英 | -233036 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 441 | 485 | 110 | 1 | 28 | 2145 | 80A | TPE-2 | 682056 |  |  | US$ | 24000 |  |  | -24000 | BM0-BM3 | [10 empty] | 電匯 CHT TPE海纜UPG#9/BM0~3作業手續費 | 閔秀英 | -682056 | 應付代收款－代收TPE#2海纜建設專款
109 | 6060 | 4 | 6160 | 6107 | 109 | 12 | 3 | 2145 | 80A | TPE-2 | 1140795 | - | AT&T US$39,892.13(手續費US$16.27) | US$ | 39892.13 |  |  |  |  | 39892.13 | [9 empty] | 代收TPE 海纜 UPGRADE#9 BM0 工程款-AT&T | 閔秀英 | 1140795 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 2531 | 2506 | 110 | 5 | 21 | 2145 | 80A | TPE-2 | 1718608 | - | KT US$60,760.39(手續費US$5.38) | US$ | 60760.39 | [6 empty] | 60760.39 | [7 empty] | 代收TPE UPGRADE#10 BM0款 -KT | 閔秀英 | 1718608 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 3002 | 2950 | 110 | 6 | 21 | 2145 | 80A | TPE-2 | 3779 | - |  | US$ | 136.29 | 136.29 | [13 empty] | 代收TPE UPG CBP利息收入(136.29) | 閔秀英 | 3779 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 3118 | 3104 | 110 | 6 | 30 | 2145 | 80A | TPE-2 | 1357542 | - | CU US$48,514.84(手續費US$30.39) | US$ | 48514.84 | [6 empty] | 48514.84 | [7 empty] | 代收TPE UPGRADE#10 BM0款 -CU | 閔秀英 | 1357542 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 3466 | 3471 | 110 | 7 | 27 | 2145 | 80A | TPE-2 | 88325 |  | CIENA日本US$3,179 | US$ | -3179 | [7 empty] | -3179 | BM0 | [5 empty] | 電匯 CIENA JAPAN TPE/UPG#10 BM0 工程代收款 | 閔秀英 | -88325 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 3467 | 3473 | 110 | 7 | 27 | 2145 | 80A | TPE-2 | 2782067 |  |  | US$ | -100132 | [7 empty] | -100132 | BM0 | [5 empty] | 電匯CIENA US TPE/UPG#10/BM0 工程代收款 | 閔秀英 | -2782067 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 3468 | 3474 | 110 | 7 | 27 | 2145 | 80A | TPE-2 | 166704 |  |  | US$ | -6000 | [7 empty] | -6000 | BM0 | [5 empty] | 電匯 CHT TPE海纜UPG#10/BM0作業手續費 | 閔秀英 | -166704 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 4482 | 4453 | 110 | 10 | 1 | 2145 | 80A | TPE-2 | 6497419 | - | KT US$234,149.65(手續費US$5.39) | US$ | 234149.65 | [6 empty] | 234149.65 | [7 empty] | 代收TPE UPG#10 BM1 USD$234,149.65-KT | 閔秀英 | 6497419 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 4785 | 4730 | 110 | 10 | 21 | 2145 | 80A | TPE-2 | 5166922 | - | CU US$186,202.10(手續費US$15.39) | US$ | 186202.1 | [6 empty] | 186202.1 | [7 empty] | 代收TPE UPG#10 BM1 USD$186,202.10-CU | 閔秀英 | 5166922 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 4836 | 4846 | 110 | 10 | 27 | 2145 | 80A | TPE-2 | 11114251 |  | CIENA US US$400,528 | US$ | -400528 | [7 empty] | -400528 | BM1 | [5 empty] | 電匯CIENA US TPE/UPG#10/BM1 工程代收款 | 閔秀英 | -11114251 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 4839 | 4847 | 110 | 10 | 27 | 2145 | 80A | TPE-2 | 383179 |  | CIENA日本US$13,808.76 | US$ | -13808.76 | [7 empty] | -13808.76 | BM1 | [5 empty] | 電匯 CIENA JAPAN TPE/UPG#10 BM1 工程代收款 | 閔秀英 | -383179 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 4842 | 4848 | 110 | 10 | 27 | 2145 | 80A | TPE-2 | 166494 |  | CHT US$6000 | US$ | -6000 | [7 empty] | -6000 | BM1 | [5 empty] | 電匯 CHT TPE海纜UPG#10/BM1作業手續費 | 閔秀英 | -166494 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5214 | 5187 | 110 | 11 | 19 | 2145 | 80A | TPE-2 | 6524194 | - | KT US$233,056.88(手續費US$5.41) | US$ | 233056.88 | [6 empty] | 233056.88 | [7 empty] | 代收TPE UPGRADE#10 BM2款 -KT | 閔秀英 | 6524194 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5297 | 5281 | 110 | 11 | 25 | 2145 | 80A | TPE-2 | 5212121 | - | CU US$186,187.08(手續費US$15.41) | US$ | 186187.08 | [6 empty] | 186187.08 | [7 empty] | 代收TPE UPGRADE#10 BM2款 -CU | 閔秀英 | 5212121 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5349 | 5369 | 110 | 12 | 6 | 2145 | 80A | TPE-2 | 11139885 |  | CIENA US US$400,528 TPE#10 BM2 | US$ | -400528 | [7 empty] | -400528 | BM2 | [5 empty] | 電匯CIENA US TPE/UPG#10/BM2 工程代收款 | 閔秀英 | -11139885 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5350 | 5370 | 110 | 12 | 6 | 2145 | 80A | TPE-2 | 353670 |  | CIENA日本US$12,716 TPE#10 BM2 | US$ | -12716 | [7 empty] | -12716 | BM2 | [5 empty] | 電匯 CIENA JAPAN TPE/UPG#10 BM2 工程代收款 | 閔秀英 | -353670 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5351 | 5371 | 110 | 12 | 6 | 2145 | 80A | TPE-2 | 166878 |  | CHT US$6000 TPE UPG#10 BM2 | US$ | -6000 | [7 empty] | -6000 | BM2 | [5 empty] | 電匯 CHT TPE海纜UPG#10/BM2作業手續費 | 閔秀英 | -166878 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5685 | 5655 | 110 | 12 | 21 | 2145 | 80A | TPE-2 | 2087 | - |  | US$ | 75.13 | 75.13 | [13 empty] | 代收TPE UPG CBP利息收入(75.13) | 閔秀英 | 2087 | 應付代收款－代收TPE#2海纜建設專款
110 | 6060 | 4 | 5239 | 5211 | 110 | 11 | 22 | 2145 | 80A | TPE-2 | 1701227 | - | KT US$60,771.14(手續費US$5.41) | US$ | 60771.14 | [6 empty] | 60771.14 | [7 empty] | 代收TPE UPGRADE#10 PROFORMA INVOICE款 -KT | 閔秀英 | 1701227 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 1044 | 1020 | 111 | 3 | 16 | 2145 | 80A | TPE-2 | 614729 | - | CU US$22,070.48 | US$ | 22070.48 | [6 empty] | 22070.48 | [7 empty] | 代收TPE UPGRADE#10 BM3款 -CU | 閔秀英 | 614729 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 1067 | 1114 | 111 | 3 | 23 | 2145 | 80A | TPE-2 | 1216140 |  |  | US$ | -43662.8 | [7 empty] | -43662.8 | D&T | [5 empty] | 電匯CIENA US TPE海纜 UPG#10/BM3 工程代收款 | 閔秀英 | -1216140 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 1069 | 1115 | 111 | 3 | 23 | 2145 | 80A | TPE-2 | 167118 |  |  | US$ | -6000 | [7 empty] | -6000 | D&T | [5 empty] | 電匯 CHT TPE海纜UPG#10/BM3作業手續費 | 閔秀英 | -167118 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 1438 | 1417 | 111 | 4 | 15 | 2145 | 80A | TPE-2 | 282442 | - | KT US$9,931.50 | US$ | 9931.5 | [9 empty] | 9931.5 |  |  |  |  | 代收TPE UPGRADE#11 BM0款 -KT | 閔秀英 | 282442 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2169 | 2155 | 111 | 6 | 21 | 2145 | 80A | TPE-2 | 6331 | - |  | US$ | 213.24 | 213.24 | [13 empty] | 代收TPE UPG CBP利息收入(213.24) | 閔秀英 | 6331 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2240 | 2217 | 111 | 6 | 27 | 2145 | 80A | TPE-2 | 884760 | - | CU US$29,794.92(手續費US15.08) | US$ | 29794.92 | [9 empty] | 29794.92 |  |  |  |  | 代收TPE UPGRADE#11 BM0款 -CU US$29,794.92 | 閔秀英 | 884760 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2333 | 2304 | 111 | 7 | 5 | 2145 | 80A | TPE-2 | 588222 | - | CU US$19,858.28(手續費US15.05) | US$ | 19858.28 | [9 empty] | 19858.28 |  |  |  |  | 代收TPE UPGRADE#11 BM0款 -CT US$19,858.28 | 閔秀英 | 588222 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2360 | 2476 | 111 | 7 | 19 | 2145 | 80A | TPE-2 | 1408419 |  |  | US$ | -47548 | [10 empty] | -47548 | BM0 |  |  | 電匯CIENA US TPE海纜 UPG#11/BM0 工程代收款 | 閔秀英 | -1408419 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2361 | 2477 | 111 | 7 | 19 | 2145 | 80A | TPE-2 | 179859 |  |  | US$ | -6072 | [10 empty] | -6072 | BM0 |  |  | 電匯CIENA JAPAN TPE海纜UPG#11 BM0工程代收款 | 閔秀英 | -179859 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2362 | 2545 | 111 | 7 | 25 | 2145 | 80A | TPE-2 | 177726 |  |  | US$ | -6000 | [10 empty] | -6000 | BM0 |  |  | 電匯 CHT TPE海纜UPG#11/BM0作業手續費 | 閔秀英 | -177726 | 應付代收款－代收TPE#2海纜建設專款
111 | 6060 | 4 | 2618 | 2592 | 111 | 7 | 27 | 2145 | 80A | TPE-2 | 2682567 | - | KT US$90,563.02(手續費剩餘US0.085) | US$ | 90563.02 | [9 empty] | 90563.02 |  | BM1 |  |  | 代收TPE UPGRADE#11 BM1預收款 -KT US$90,563.02 | 閔秀英 | 2682567 | 應付代收款－代收TPE#2海纜建設專款
[15 empty] | 164002.51 | 424.66 |  |  |  | 39892.13 | 0 | 1031712.56 | -998554.56 |  | 150147.72 | -59620 |  | 0 | 0
[14 empty] | Diff | 0 | 424.66 |  |  |  | 39892.13 | 0 | 1031712.56 | -998554.56 |  | 150147.72 | -59620 |  | 0 | 0
[14 empty] | Balance | 163577.85 | [5 empty] | 39892.13 |  | 33158 |  |  | 90527.72 |  |  | 0
[14 empty] | 收 | 1221752.41
[14 empty] | 付 | -1058174.56
40.9888

## Ciena Invoice (UPG#10) (hidden)
Ciena's Invoices |  |  | Total
BM0 | 100132 | 3179 | 103311
BM1 | 400528 | 12716 | 413244
BM2 | 400528 | 12716 | 413244
|  | Total | 929799
Ciena's Invoices
Japan tax |  |  | 507.98
Japan tax |  |  | 507.98
Reimbursement of taxes for Japan/Taiwan/China |  |  | 42646.84
|  | Total | 43662.8
|  | Sub-Total | 973461.8

## Cashflow (UPG#11) (hidden)
[Unit: USD]
| Percentage | Forecasted Month of Billing | Supply Contract Cost | Non-supply Contract Cost (Duty, tax etc..) | Total | Surplus Upgrade
PC20 |  |  | 530684 | 63343.2293 | 594027.2293
BM0 | 10% |  | 53068 | 552 | 53620
BM1 | 40% |  | 212274 | 2208 | 214482
BM2 | 40% |  | 212274 | 2208 | 214482
BM3 | 10% |  | 53068 | 5306.8 | 58374.8
D&T |  |  |  | 53068.4293
|  | UPG#11 | 2022.03 (BM0) |  |  |  | 2022_11 (BM1) |  |  |  | 2022_07 (BM2) |  |  |  | 2022_07 (BM3) |  |  |  | 2022_xx (D&T, etc)
No. | Party | Liability_v1 (In Percentage) | BM0 (SC Cost) | BM0 (NSC Cost) | CBP | Sub-total | BM1 (SC Cost) | BM1 (NSC Cost) | CBP | Sub-total | BM2 (SC Cost) | BM2 (NSC Cost) | CBP | Sub-total | BM3 (SC Cost) | BM3 (NSC Cost) | CBP | Sub-total | D&T, etc. | CBP | Sub-total
1 | CT | 33.33% | 17689.3333 | 184 | 2000 | 19873.3333 | 70758 | 736 | 2000 | 73494 | 70758 | 736 | 2000 | 73494 | 17689.3333 | 1768.9333 | 2000 | 21458.26 | 17689.4764 | 2000 | 19689.4764
2 | CU | 50% | 26534 | 276 | 3000 | 29810 | 106137 | 1104 | 3000 | 110241 | 106137 | 1104 | 3000 | 110241 | 26534 | 2653.4 | 3000 | 32187.4 | 26534.2146 | 3000 | 29534.2146
3 | CHT | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | NTT-LJ | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | KT | 16.67% | 8844.6667 | 92 | 1000 | 9936.6667 | 35379 | 368 | 1000 | 36747 | 35379 | 368 | 1000 | 36747 | 8844.6667 | 884.4667 | 1000 | 10729.14 | 8844.7382 | 1000 | 9844.7382
6 | Verizoon | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | AT&T | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 100% | 53068 | 552 | 6000 | 59620 | 212274 | 2208 | 6000 | 220482 | 212274 | 2208 | 6000 | 220482 | 53068 | 5306.8 | 6000 | 64374.8 | 53068.4293 | 6000 | 59068.4293
[13 empty] | UPG#11 BM1~2 | 440964
500584
[13 empty] | KT's Proforma Invoice for BM1~3 | 90568.04
[13 empty] | BM1 | 36747
[13 empty] | BM2 | 36747
[13 empty] | KT's invoice Balance Amount | 17074.04

## Contact (hidden)
Party | Company Name | ATTN | ADDR | E-mail | Tel
NTT-LJ | NTT Ltd Japan Corporation | Mr. Takuto Nishi Mr. Yuichi Sugita | OTEMACHI PLACE WEST TOWER, 2-3-1 Otemachi Chiyoda-ku, Tokyo, 100-0004, Japan | t.nishi@ntt.com yuichi.sugita@ntt.com | t.nishi@ntt.com yuichi.sugita@ntt.com
KT | KT Corporation Global Network Planning Unit | Seungdeok Han (한승덕) | 65, Daehak-ro, Jongno-gu, Seoul, Korea | seungdeok.han@kt.com | Tel.: +82-10-7300-5034
CU | China United Network Communications Group Company Limited, International Dept. | Mr. Wang Kai | No 21 Jinrong St., Xicheng District, Beijing 100033 | wangkai@chinaunicom.cn | Tel.: +86-10-66259017 +86-15611112768
CT | China Telecom Corporations Network Planning and Construction Department | Mr. Pengkui Chu | No. 19 Chaoyangmen Beidajie, Beijing, 100010 | chupk@chinatelecomglobal.com | Tel: +86-10-59501081